## Gantt
Project Gantt — Integrated Probabilistic Forecasting of Electricity Demand & Renewable Generation (12-Month Plan)
NOGA ISO R&D 2027 • PIs: Or Aleksandrowicz, Avigdor Gal (Technion) • Assumed duration: 12 months • Bars = active months; ◆ = milestone
Work Package / Task | Start | End | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
WP1 — Data Collection & Open Benchmark (Task 1)
Project kick-off, data agreements & access | M1 | M1
Augment dataset: renewable (PV/wind), reserve/balancing indicators | M1 | M3
Exogenous drivers: weather, calendar & special-day features | M2 | M3
Release reproducible benchmark with fixed splits | M3 | M4
WP2 — Calibrated Probabilistic Demand Forecasting (Task 2)
Develop probabilistic demand models (quantile/density/non-param.) | M3 | M6
Distribution-free calibration layer (coverage guarantees) | M5 | M7
Benchmark vs NOGA operational baseline (scoring + cost) | M6 | M7
WP3 — Probabilistic Renewable-Generation Forecasting (Task 3)
Adapt models to bounded, diurnal PV & wind regimes | M4 | M7
Calibration & proper-scoring evaluation | M6 | M8
WP4 — Integration into Net-Demand Distribution (Task 4)
Marginal coupling with estimated dependence | M7 | M9
Joint demand-renewable modelling | M8 | M10
Compare strategies: skill, scenarios, operational cost | M9 | M10
WP5 — Risk-Aware Decision Layer & Validation (Task 5)
Cost-optimal decision layer (newsvendor / numerical) | M9 | M11
Operational validation vs current NOGA forecast | M10 | M11
Deployable prototype & knowledge transfer to NOGA | M11 | M12
WP6 — Management & Dissemination
Project management & periodic reporting | M1 | M12
Publications & dissemination | M6 | M12
Final report & milestone reviews | M12 | M12
Milestones |  |  | ◆ |  |  | ◆ |  |  | ◆ |  |  | ◆ |  | ◆
Milestone key:
M1 Kick-off M4 Benchmark M7 Models calibrated M10 Integration M12 Prototype+Report